PROJECT 2

Predictive AI Monitoring Platform

Goal: Build an enterprise observability tool that ingests high-throughput telemetry streams via Redpanda/Kafka, routes data to ClickHouse, runs Python Isolation Forest ML models to predict failures, and streams alerts to a React dashboard via WebSockets.

Improvement Notes — read before you start Week 1 • No labeled evaluation set for the Isolation Forest. Inject known, labeled anomalies into your synthetic data so you can report precision/recall, not just an anomaly-score threshold. • The '30-minutes-in-advance' claim needs a concrete mechanism. Name the specific feature (e.g. memory growth slope) that drives lead time, or it won't survive a defense Q&A. • The Topology page promises a Model Health & Drift panel, but there's no backend task to actually compute drift or trigger retraining — the UI would show numbers with nothing behind them. Add a scheduled drift-recompute job. • Kafka offset commits aren't tied to ClickHouse write success. If a ClickHouse batch insert fails after the offset is committed, that data is lost silently. Commit offsets only after a successful write (at-least-once delivery). • WebSocket connections have no auth — fine for a solo demo, but call this out explicitly as a scope cut rather than leaving it unaddressed. • The 60 FPS / 100+ msgs/sec target should be validated against real setOption() cost in ECharts, not assumed free just because refs are used. Batch to one setOption call per 500ms tick.

# Frontend Architecture & Anti-AI Design Rules

Required Pages

☐ /dashboard — Live Command Center (40% Predictive Alert Feed | 60% 2×2 Telemetry Metric Grid).

☐ /incidents/:id — Incident Root-Cause Inspector (Synchronized timeline cursor + Monospace Log Terminal).

☐ /topology — Service Dependency Graph + ML Model Health & Baseline Drift Panel.

Technical Constraints

☐ Circular Buffers: Max 500 data points per chart in browser memory (oldest points dropped automatically).

☐ DOM Decoupling: Apache ECharts managed imperatively via useRef to bypass React's Virtual DOM.

☐ Stream Controls: "Freeze Feed" button to pause WebSocket updates while inspecting spikes.

Anti-AI Design System

| Element | Spec |
| --- | --- |
| Color — Canvas | Canvas #0d0e11 |
| Color — Panel | Panel #16181d |
| Color — Border | Border #23272e |
| Color — Status | Green #10b981 / Amber #f59e0b / Red #ef4444 |
| Typography — UI | Inter for UI headers |
| Typography — Mono | JetBrains Mono for server names, latency metrics, and log outputs |

Strict No-Go • Zero glassmorphism • No rounded pastel cards • No floating AI sparkles

WEEK 1 — Data Ingestion & Streaming Infrastructure

Day 1: Synthetic Telemetry Generator

☐ Write a script generating mock server metrics (CPU, Memory, Error rates) with timestamps.

– Improvement: inject a known set of labeled anomalies alongside normal data for later precision/recall scoring.

Day 2: Redpanda / Kafka Setup

☐ Spin up Redpanda container via Docker Compose.

☐ Create a telemetry topic and publish mock metric events to it.

Day 3: ClickHouse Data Layer

☐ Spin up ClickHouse container with time-series schema.

☐ Write consumer service to micro-batch write Kafka data into ClickHouse.

## Week 1 Definition of Done (Validation Test)

Telemetry generator publishes 1,000+ metrics/sec to Redpanda. ClickHouse consumer service ingests them in micro-batches without dropping messages, verified via SELECT count() FROM telemetry in ClickHouse.

Common AI Bugs to Watch Out For • ClickHouse Single-Row Inserts ("Too Many Parts" Error): an insert per individual Kafka event will crash with Too many parts in partition. Batch writes in 1,000-row chunks. • Kafka Consumer Group Offset Loops: forgetting to commit offsets or misconfiguring auto.offset.reset causes the worker to re-read the entire log history on every restart.

WEEK 2 — Machine Learning Anomaly Detection

Day 4: Feature Engineering

☐ Calculate rolling averages and standard deviations over time-series metric windows.

Day 5: Isolation Forest Model

☐ Train a scikit-learn Isolation Forest model on historical metric baselines.

☐ Output an anomaly score for incoming real-time metric streams.

Day 6: Predictive Lead-Time Logic

☐ Build threshold rules (e.g., memory growth rate trends) to flag failure warnings 30 minutes in advance.

– Improvement: pin down the exact feature driving the lead-time claim so it can be defended, not just demoed.

## Week 2 Definition of Done (Validation Test)

Injecting CPU/Memory spikes into the stream triggers the Python Isolation Forest model to return anomaly scores >0.75, emitting a predictive alert payload 30 minutes before simulated system failure. Precision/recall against the labeled anomaly set should also be reported.

Common AI Bugs to Watch Out For • Model Retraining in the Ingestion Loop: putting IsolationForest.fit() inside the real-time stream consumer loop. Pre-train the model; the real-time path should strictly call predict / decision_function. • Data Leakage in Rolling Windows: calculating rolling standard deviations using future data points instead of restricting to past timestamp observations.

WEEK 3 — Real-Time API & Query Layer

Day 7: Node.js WebSocket Server

☐ Setup WebSocket server to listen to ML prediction outputs.

☐ Implement bi-directional ping/pong heartbeat and message broadcasting.

Day 8: ClickHouse Baseline Query Optimization

☐ Write ClickHouse queries comparing live metrics against historical 10M+ row baselines.

## Week 3 Definition of Done (Validation Test)

WebSocket server broadcasts alerts to clients in <50ms. ClickHouse baseline queries against 10M+ historical records execute in <150ms.

Common AI Bugs to Watch Out For • Missing WebSocket Heartbeats: raw WebSocket handlers without ping/pong leave "zombie" TCP connections alive when clients disconnect or switch networks. • PostgreSQL Syntax in ClickHouse: generating standard PostgreSQL syntax (e.g. unsupported foreign keys or subqueries) that ClickHouse doesn't support.

WEEK 4 — Multi-Page SRE Dashboard Frontend & Performance Tuning

Day 9: Live Command Center (/dashboard)

☐ Build 40/60 split view: Predictive Alert List sorted by time-to-failure + 2×2 ECharts Telemetry Grid.

☐ Add "Freeze Feed" stream control button.

Day 10: Root-Cause Inspector (/incidents/:id)

☐ Build synchronized crosshair cursor across stacked metric charts.

☐ Build Monospace Log Terminal (#090a0f background) with "Show Anomalies Only" toggle.

Day 11: System Topology Page (/topology)

☐ Build service dependency graph showing health status per node.

☐ Build ML Model Health panel (showing Drift %, Precision, and Average Lead Time).

– Improvement: back this panel with an actual scheduled drift-recompute job, not static/mock numbers.

Day 12–14: Performance Profiling & Defense Practice

☐ Verify 60 FPS rendering under 100+ WebSocket msgs/sec using Chrome DevTools.

☐ Practice explaining row vs. columnar database tradeoffs out loud.

## Week 4 Definition of Done (Validation Test)

Navigating across all 3 pages (/dashboard, /incidents/:id, /topology) works seamlessly. The frontend receives 100+ WebSocket metric updates per second, maintaining 60 FPS performance without frame drops or memory leaks, while circular buffers keep browser memory flat.

Common AI Bugs to Watch Out For • State Update React Crash: putting every incoming WebSocket message directly into React state triggers ~50 Virtual DOM re-renders per second at 50 msgs/sec, freezing the tab. Batch state updates every 500ms and use useRef for chart references. • Chart Memory Leaks: initializing echarts.init() inside a component body without calling chart.dispose() in the useEffect cleanup function fills browser memory on page navigation.